## Slide 1
PROJECT PLANNING DECK
Payment Disbursement System
Java Migration
Delivery roadmap, resourcing model & governance for the modernization of the legacy payments platform.
TIMELINE
Q3 2026 – Q1 2028
DELIVERY MODEL
Phased migration
RESOURCING SHIFT
TCS → FTE · Jun 2027

## Slide 2
EXECUTIVE SUMMARY
Project at a Glance
18
MONTHS
End-to-end delivery
5
PHASES
Discovery to hypercare
~30
PEAK TEAM
Blended onshore/offshore
Q4 2027
GO-LIVE
Production cutover window
PROGRAM OVERVIEW
The Payment Disbursement System will be re-platformed from the legacy monolith to a modern, cloud-ready Java stack (Java 21, Spring Boot microservices). The migration is delivered in phases to de-risk cutover of business-critical payment flows while keeping the existing platform fully operational.
Delivery begins with a TCS contractor-led build team and transitions in June 2027 to a permanent, in-house model led by full-time employees and the offshore GCC.
KEY OBJECTIVES
Modernize & scale
Microservices for higher throughput and resilient disbursements
Strengthen compliance
Auditability, security and regulatory alignment by design
Reduce tech debt
Retire legacy dependencies and lower run-cost
Build internal capability
Hand delivery and run to FTE + GCC teams

## Slide 3
OPERATING MODEL
Two-Phase Resourcing Strategy
The delivery team transitions from a TCS contractor build squad to a permanent FTE-led model at the June 2027 milestone, shifting capability and run ownership in-house.
PHASE 1
TCS Contractor Build Team
Project start → June 2027
Chart: 
| Offshore | Onshore
mix | 67 | 33
33%
TCS onshore contractors
67%
TCS offshore contractors
JUN
2027
HANDOVER
PHASE 2
FTE-Led Permanent Model
July 2027 → Run & operate
Chart: 
| Offshore GCC | Onshore FTE
mix | 70 | 30
30%
Onshore full-time employees
70%
Offshore GCC resources

## Slide 4
OPERATING MODEL
Resource Mix Across the Delivery Window
Indicative blended headcount by quarter. The team composition shifts from TCS contractors to FTE + GCC resources around the June 2027 handover.
Chart: Headcount
| Q3'26 | Q4'26 | Q1'27 | Q2'27 | Q3'27 | Q4'27 | Q1'28
TCS Onshore | 4 | 6 | 7 | 7 | 2 | 0 | 0
TCS Offshore | 8 | 12 | 14 | 14 | 4 | 0 | 0
FTE Onshore | 0 | 0 | 0 | 0 | 6 | 7 | 6
GCC Offshore | 0 | 0 | 0 | 0 | 14 | 17 | 14
TRANSITION PRINCIPLES
1
1
Knowledge transfer
Structured KT runs in the 2 quarters before handover.
2
2
No delivery gap
FTE/GCC ramp overlaps TCS rampdown to protect velocity.
3
3
Run ownership
Support & run move fully in-house post Jun 2027.
4
4
Capacity steady
Peak ~30 FTE-equivalent maintained through cutover.

## Slide 5
PLAN
Delivery Roadmap
Q3'26
Q4'26
Q1'27
Q2'27
Q3'27
Q4'27
Q1'28
Discovery & Assessment
Architecture & Foundation
Core Migration — Build
Cutover & Migration
Stabilization & Hypercare
Knowledge Transfer (KT)
Jun 2027 — Resourcing handover
TCS-led build
FTE/GCC-led
Assess / stabilize
Knowledge transfer

## Slide 6
SCOPE
Migration Workstreams
WS1
Disbursement Engine
Re-platform core payment orchestration & scheduling logic.
WS2
Payment Rails & Gateways
Re-integrate ACH, wire, RTP and card-network connectors.
WS3
Reconciliation
Rebuild matching, settlement and exception handling.
WS4
Data Migration
Migrate historical ledgers with integrity validation.
WS5
Integration & APIs
Expose modern REST/event APIs to upstream systems.
WS6
Security & NFRs
Encryption, access control, performance & resilience.

## Slide 7
GOVERNANCE
Workstream Status Dashboard
Indicative baseline plan view — RAG health, ownership and phase readiness across delivery workstreams.
WORKSTREAM
OWNER
PHASE
PROGRESS
HEALTH
Disbursement Engine
A. Mehta (TCS)
Build
45%
Payment Rails & Gateways
R. Khanna (TCS)
Build
30%
Reconciliation
S. Iyer (TCS)
Design
20%
Data Migration
L. Park (FTE)
Design
15%
Integration & APIs
J. Alvarez (TCS)
Build
35%
Security & NFRs
M. Okafor (FTE)
Assess
10%
On track
At risk
Off track

## Slide 8
GOVERNANCE
Key Risks & Mitigations
1
Payment continuity during cutover
Mitigation: Phased, reversible cutover with parallel-run and rollback playbooks.
High
2
Knowledge loss at TCS → FTE handover
Mitigation: Structured KT from Q1'27; shadowing & runbooks before Jun 2027.
Med
3
Data integrity on ledger migration
Mitigation: Automated reconciliation & dual-write validation gates.
Med
4
GCC ramp-up capacity
Mitigation: Early hiring pipeline; overlap with TCS to protect velocity.
Med
5
Third-party rail integration delays
Mitigation: Vendor engagement in discovery; sandbox certification early.
Low

## Slide 9
NEXT 90 DAYS
Immediate Next Steps
01
Mobilize TCS build squad
Onboard onshore/offshore contractors; stand up environments.
02
Finalize target architecture
Lock Java 21 / Spring Boot reference design & guardrails.
03
Confirm KT & transition plan
Lock Jun 2027 handover scope, GCC hiring & FTE roles.
04
Baseline governance & RAG
Stand up status dashboard, risk log and cadence.
Payment Disbursement System · Java Migration Program
Resourcing handover: June 2027